## market_place
End Point | Method | status | response | error | comments
https://localfete.com/home/design | get | 200 | home pafe | Console.log(error) | Review the home page from top to bottom, check if every single link is working etc
social media links |  |  |  |  | the social media accounts have not been created yet
https://localfete.com/becomeseller | get | 200 | become seller page | Console.log(error) | This page only shows static page related to become a seller. Please check the video is working
https://localfete.com/stores | get | 200 | stores page + data in json | Console.log(error) | This page will display all the store activate
https://localfete.com/subcategory/{subcategory_name} | get | 200 | subcategory page + data in json | Console.log(error) | Check the burguer menu on top left. Check if the subcategory shows de products
https://localfete.com/stores/borough/${boroughname} | get | 200 | data.stores in json data.events in json | Console.log(error) | The platform will display the boroughs and Events related to the area that de user is loking for
https://localfete.com/products/productborough/${borough}/${product} | get | 200 | products in json | Console.log(error) | the platfom will display the products that the user is loking for
https://localfete.com/stores/vendor/${store_name} | get | 200 | products in json | Console.log(error) | the store details is display with php and the products with javascript
https://localfete.com/cart/user | get | 200 | products in cart in json | Console.log(error) | The platform will display all the products in the shopping cart
https://localfete.com/products/article/spring-dress | get | 200 | single product or variable product in json | Console.log(error) | The platform will display product standard or variable product. Please check every single section on the page. Gallery, video, add the product, description and comments

## report_marketplace
Localfete QA Test Report-Market_place
Test Case |  | LocalFete | Test Case Description | Local Fate website QA and Test |  | All Bug Folder
Created and Developed By |  | Victor | Tested & Reviewed By | Fardin Amin Arpon |  | Version: 1st Release
Tester's Name |  | Fardin Amin | Date Tested | 2022-02-24 | Test Case (Pass/Fail/Not Executed) |  | Pass 7/10
Scenario | Test Case Id | Title | Steps/Actions | Test Data/Endpoint | Expected Result | Actual Result | Bug Doc. |  | 2022-03-05
LocalFete QA¦Test Market- Place Report | Test_01 | Review the home page from top to bottom, check if every single link is working etc | 1.Visit the application "EndURL" then cheek all the page review | https://localfete.com/home/design | All the UI and Responsive work properly | Takes more area in the right side UI issus, plsase Shift in the middle | UI Bug 1 photo | Phone bug | fixed | fixed responsivefor logn and register pages
| Test_02 | Social media links Cheek | 1. Visit the application "EndURL" 2. cheek all the socail media link working properly | https://localfete.com/home/design | social media links working propely | socal media account did not create yet | Bug pic |  | The social links have not created yet
| Test_03 | Become seller page | 1. Visit the application "EndURL" 2. Click on the Video. 3. Cheek UI and All Element working properly | https://localfete.com/becomeseller | This page only shows static page related to become a seller.video is working | As Expected
| Test_04 | This page will display all the store activate | 1. Visit the application "EndURL" 2. Cheek all the store icon btn 3. Cheek UI and All Element | https://localfete.com/stores | This page will display all the store activate | As Expected
| Test_05 | User can logged in through facebCheck the burguer menu on top left. Check if the subcategory shows the productstore | 1. Visit the application "URL" 2. Click on the "Select the burguer menu btn" 3. Cheek one a item and its subcategory in the productstore | https://localfete.com/subcategory/cellphones_accessories | Check if the subcategory shows the productstore | As expected
| Test_06 | The platform will display the boroughs and Events related to the area that the user is loking for | 1. Visit the application "URL" 2. Search the item what are looking for | https://localfete.com/stores/borough/${boroughname} | Need help button should redirect the user to login help page | As expected
| Test_07 | the platfom will display the products that the user is loking for | 1. Visit the application "URL" 2. Search the item what are looking for | https://localfete.com/products/article/iphone-xs | User should redirect to the signup page | As expected
| Test_08 | the store details is display with php and the products with javascript | 1. Visit the application "URL" 2. cheek store details is display with php and the products with javascript | https://localfete.com/stores/vendor/${store_name} | cheek store details is display with php and the products with javascript | As expected
| Test_09 | The platform will display all the products in the shopping cart | 1. Visit the application "URL" 2. Login in as a buyer user 3. Bought some Itme form store 4. Goto the cart icon 5. look all the item display on the cart | https://localfete.com/cart/user | System should show the detaild information1 on the cart | As expected
| Test_10 | The platform will display product standard or variable product. Please check every single section on the page. Gallery, video, add the product, description and comments | 1. Visit the application "URL" 2. User clicks on any link of page footer | https://localfete.com/products/article/spring-dress | System should redirect user to the relevent page | Failed | Bug pic | done

## user
End Point | Method | status | Response | Error | Comments | Bug
https://localfete.com/user/register | get | 200 | Registration page | Console.log (error) | It displays the registration form which the user can select the profile buyer or vendor. Please verify if there is any security gap
https://localfete.com/user/welcome | get | 200 | Welcome Page | Console.log (error) | This page asks the user to activate their account via email
https://localfete.com/user/login | get | 200 | Login Page | Console.log (error) | Please check if there is any security gap in the login form
https://localfete.com/user/password | get | 200 | Recover Password Page | Console.log (error) | The user has to type the email used in the registration. If the verification is ok it will redirect to another `
https://localfete.com/user/changePassword?email={email} | get | 200 | Verify your Email to change the Password page | Console.log (error) | If the email is registered and the status is 1 the user will be asked to verify the email to update the password
https://localfete.com/user/ updatePassword?email={email} &token={token} | get | 200 | Update Password page | Console.log (error) | The user has to type the new password twice. Please check if there is any security gap in the change password form
https://localfete.com/user/ validateEmail/{emailaddress} | get | 200 | 1 -> email exits 0-> email does not exit | Console.log (error) | Review the home page from top to bottom, check if every single link is working etc
https://localfete.com/user/createUser | get | 200 | 1 ->user created 0-> the user could not be created | Response.text() | If the user was created it will redirect to the welcome page
https://localfete.com/user/ activate/{email}/{token} | get | 200 | 1 active 0 no active | Console.log (error) | If the user is active it will redirect to the welcome page login
https://localfete.com/user/ Log_In | Post | 200 | 1 ->admin redirect dashboard admin 2-> seller redirect dashboard seller 3-> buyer redirect home page 0-> the user has not been activated 4->Account Deleted | Console.log (error) | According to the response the platform will redirect to the respective dashboard or it will the responses the user has not been activated or the user does not exits

## report_User
f
Test Case |  | LocalFete | Test Case Description | Local Fate website QA and Test |  |  | All Bug Folder |  | Date
Created and Developed By |  | Victor | Tested & Reviewed By | Fardin Amin Arpon |  |  | Version: | 1st Release | 2022-03-03 | 2022-03-06
Scenario | TestCase Id | Title | Steps/Actions | Data/Endpoint | Response | Expected Result | Actual Result | Bug Doc. | Suggestion | Fix | Recheek
LocalFete QA¦Test User Report | Test_01 | It displays the registration form which the user can select the profile buyer or vendor. Please verify if there is any security gap | 1.Visit the application "EndURL" 2. then cheek all the page review verify | https://localfete.com/user/register | 200 | Registration page with proper security | character value limitation not provide | Bug Video | We need to add word limit It kills database memory also secuity issue. Beside we can add localFete logo and Eye icon in password section for better UI Expr. | fixed. Verify if in google chrome works | please add Eye Icon in password section
| Test_02 | This page asks the user to activate their account via email | 1. Visit the application "EndURL" 2. cheek link working properly 3. cheek Massage showing properly or not | https://localfete.com/user/welcome | 200 | Active their Accout Welcome Page | As Expected | photo | we we can add localFete logo for better UI Expr. | fixed | Done
| Test_03 | Please check if there is any security or UI gap in the ""login form"" | 1. Visit the application "EndURL" 2. cheek login link working properly 3. cheek Massage with UI | https://localfete.com/user/login | 200 | Login Page | As Expected But need add logo and more space | photo | need some more gap of two module. and also add eye icon and logo | fixed | Done
| Test_04 | The user has to type the email used in the registration. If the verification is ok it will redirect to another | 1. Visit the application "EndURL" 2. Cheek link working properly or not 3. Cheek UI and All Element | https://localfete.com/user/password | 200 | Recover Password Page | As Expected But need some changes | photo | we we can add localFete logo for better UI UX. | fixed | Done
| Test_05 | If the email is registered and the status is 1 the user will be asked to verify the email to update the password. | 1. Visit the application "URL" 2. Give register mail data 3. Then a mail come on inbox 4. cheek mail link | https://localfete.com/user/changePassword?email={email} | 200 | Verify your Email to change the Password page Cheek mail link | As Expected | photo
| Test_06 | The user has to type the new password twice. Please check if there is any security gap in the change password form | 1. Visit the application "URL" 2. Search the item what are looking for | https://localfete.com/user/ updatePassword?email={email} &token={token} | 200 | Update Password page | As Expected But need some changes | photo | We need to add Charecter limit for database & security issud, and also "eye" icon for see pass when give input besides need to add word limitation and add logo | fixed
| Test_07 | Review the home page from top to bottom, check if every single link is working etc | 1. Visit the application "URL" 2.Check homepage | https://localfete.com/user/ validateEmail/{emailaddress} | 200 | 1 -> email exits 0-> email does not exit | As expected | As expected
| Test_08 | If the user was created it will redirect to the welcome page | 1. Visit the application "URL" 2. Try to create a new user with same mail which already have created 3. it show redirect to the welcome page | https://localfete.com/user/createUser | 200 | 1 ->user created 0-> the user could not be created | As expected | As expected
| Test_09 | If the user is active it will redirect to the welcome page login | 1. Visit the application "URL" 2. Login in as a buyer user 3. Bought some Itme form store 4. Goto the cart icon 5. look all the item display on the cart | https://localfete.com/user/ activate/{email}/{token} | 200 | 1 active 0 no active | As Expected | As Expected
| Test_10 | According to the response the platform will redirect to the respective dashboard or it will the responses the user has not been activated or the user does not exits |  | https://localfete.com/user/ Log_In | 200 | 1 ->admin redirect dashboard admin 2-> seller redirect dashboard seller 3-> buyer redirect home page 0-> the user has not been activated 4->Account Deleted

## Buyer
End Point | Method | status | response | error | comments
https://localfete.com/buyer/admin | get | 200 | index page | console.log(error) | check if you can see the totalof number of products and disputes
https://localfete.com/buyer/profile | get | 200 | profile form | console.log(error) | check if you can update the profile form and also if there are security gaps
https://localfete.com/buyer/orders | get | 200 | buyer orders | console.log(error) | check if you can see the orders. For doing that you have to buy a product
https://localfete.com/buyer/orderdetail/{detai id} | get | 200 | detail orders | console.log(error) | check if you can see the detail of the orders. For foing that you have to buy a product
https://localfete.com/buyer/disputes | get | 200 | buyer diputes | console.log(error) | check if you can see the disputes. for doing that create a dispute and also verify if there are surity gaps in the form
https://localfete.com/buyer/disputedetails/{dispute id} | get | 200 | detail disputes | console.log(error) | check if you can see the detail of the dispute and also if you can give a response. Verify if there are security gaps in the form
Bell notification |  |  | bell with counter |  | Verify if you get a bell notification on top right when the seller gives a response from your dispute. You can check it when you do the seller test
https://localfete.com/home/design | get | 200 | market place home page | console.log(error) | verify if you can open the marketplace from buyer dashboard
http://localfete.com/buyer/delete | get | 200 | delete account form | console.log(error) | verify if you can delete your account and also if thereis a security gap in the form
https://localfete.com/user/logout | get | 200 | close user session | console.log(error) | Verify if you can logout from the dashboard

## Report_Buyer
Localfete QA Test-->Report_Buyer
Test Case |  | LocalFete | Test Case Description | Local Fate website QA and Test_Buyer Section |  |  | All Bug Folder |  | Date | date
Created and Developed By |  | Victor | Tested & Reviewed By | Fardin Amin Arpon |  |  | Version: | 1st Release | 2022-03-08 | 2022-03-10
Scenario | TestCase Id | Title | Steps/Actions | Data/Endpoint | Response | Expected Result | Actual Result | Bug Doc. | Suggestion | Fixed
LocalFete QA¦Test Buyer Report | Test_01 | check if you can see the totalof numberof products and disputes | 1.Visit the application "EndURL" 2. then cheek all the page review verify | https://localfete.com/buyer/admin | 200 | index page | As Expected
| Test_02 | check if you can update the profile form and also if there are security gaps | 1. Visit the application "EndURL" 2. cheek link working properly 3. Click on update profile 4. cheek working or not | https://localfete.com/buyer/profile | 200 | profile form | Remove Password section | photo | Please remove the password section. If the user needs to change his password, he will change the password from "Change Password" option by sending update password massage in his Email. It gives more security in the account | Fixed
| Test_03 | check if you can see the orders. For doing that you have to buy a product | 1. Visit the application "EndURL" 2. cheek login link working properly 3. cheek Massage with UI | https://localfete.com/buyer/orders | 200 | buyer orders | As Expected | photo | in "orders" we can change colour and bold for better UI | Fixed
| Test_04 | check if you can see the detail of the orders. For foing that you have to buy a product | 1. Visit the application "EndURL" 2. Cheek link working properly or not 3. Cheek UI and All Element | https://localfete.com/buyer/orderdetail/{detai id} | 200 | detail orders | As Expected | photo | in "order details" we can change colour and bold for better UI | Fixed
| Test_05 | check if you can see the disputes. for doing that create a dispute and also verify if there are surity gaps in the form | 1. Visit the application "URL" 2. Give register mail data 3. Then a mail come on inbox 4. cheek mail link | https://localfete.com/buyer/disputes | 200 | buyer diputes | Box broke | photo | We need to add Charecter limit for database & security issud, it borke the box araa also so neet to break 2nd line also besides we can"dispute" colour change for better UI | Fixed
| Test_06 | check if you can see the detail of the dispute and also if you can give a response. Verify if there are security gaps in the form | 1. Visit the application "URL" 2. Search the item what are looking for | https://localfete.com/buyer/disputedetails/{dispute id} | 200 | detail disputes | detail disputes could't see for broken issuefix the Box area | photo | Please fix the box borken issue, either you give Subject charecter limit or you add 2nd line without it borke the box and we couldn't see any details list | Fixed
| Test_07 | Verify if you get a bell notification on top right when the seller gives a response from your dispute. You can check it when you do the seller test | 1. Visit the application "URL" 2.Check homepage | Bell notification | 200 | bell with counter | As Expected | As expected
| Test_08 | verify if you can open the marketplace from buyer dashboard | 1. Visit the application "URL" 2. Try to create a new user with same mail which already have created 3. it show redirect to the welcome page | https://localfete.com/home/design | 200 | market place home page | As expected | As expected
| Test_09 | verify if you can delete your account and also if thereis a security gap in the form | 1. Visit the application "URL" 2. Login in as a buyer user 3. Bought some Itme form store 4. Goto the cart icon 5. look all the item display on the cart | http://localfete.com/buyer/delete | 200 | delete account form | Ask to give password | bug photo | please add password section when they click on to delete account button. as you see Facebook, Instagram, and lot of big company ask their password for delete account . it is a big security issue for User Data Security. | Fixed
| Test_10 | Verify if you can logout from the dashboard |  | https://localfete.com/user/logout | 200 | close user Session | As Expected | As expected

## Seller
End Point | Method | status | response | error | comments
https://localfete.com/seller/admin | GET | 200 | index page | console.log(error) | check if you can see the total of products, orders and disputes. The design will be changed by tomorrow
https://localfete.com/seller/profile | GET | 200 | profile vendor | console.log(error) | check if you can update the profile form and also if there are security gaps
https://localfete.com/seller/store | GET | 200 | profile store | console.log(error) | check if you can update the profile store form and also if there are security gaps
https://localfete.com/stores/vendor/{store_name} | GET | 200 | store page | console.log(error) | after updating the profile store you will be able to see the store page
https://localfete.com/seller/products | GET | 200 | products page | console.log(error) | you will se all the products with pagination and also three call actions on the right side: view, edit and delete product
https://localfete.com/products/article/{product_name} | GET | 200 | single product page | console.log(error) | you will see the single product page it can be simple or variable. Please click in every section including the tabs at the bottom section
https://localfete.com/seller/editproduct/{product_id} | GET | 200 | Edit Product Page | console.log(error) | you will see at the right of every product three buttons: First: Open the product in a new tab second: Edit the product it can be simple or variable Third: Delete the product. Try to delete both type of products
https://localfete.com/seller/removeproduct/{product_id} | GET | 200 | Remove Product | console.log(error) | From seller product page: https://localfete.com/seller/products You will be able to delete any product clicking on the button with trush icon. Please verify if it works with both type of products
https://localfete.com/seller/productsimple | GET | 200 | create simple product page | console.log(error) | Please create a simple product including gallery and video. Check if there are security gaps in the form
https://localfete.com/seller/productvariable | GET | 200 | create variable product page | console.log(error) | You will be able to create the variable product in two parts: 1. General information. Please check security gaps in the form 2. Add products to the inventory. Please check security gaps in the form
https://localfete.com/seller/orders | GET | 200 | orders page | console.log(error) | you will see the seller's orders. On the right side you can download the order and the delivery status. Try to download t he order and also open the delivery status
https://localfete.com/seller/statusdelivery/{store_id}/{order_id} | get | 200 | Delivery Page | console.log(error) | Yu will see the status delivery of the product. Also you will be able to change the status. Try to change the status of the product
https://localfete.com/seller/disputes | GET | 200 | disputes page | console.log(error) | You will se the seller's disputes. On the right side you can click the button to see the detail of the dispute.
https://localfete.com/seller/disputedetails/{dispute_id} | GET | 200 | dispute detail page | console.log(error) | You will see the detail of the dispute and also you can reply it. Please check security gaps in the form
https://localfete.com/seller/delete | POST | 200 | delete account page | console.log(error) | You will be able to delete the seller account
https://localfete.com/products/updateSimple | POST | 200 | edit simple product page | console.log(error) | you will be able to update the simple product. Please security gaps in the form
https://localfete.com/products/updateVariable | POST | 200 | edit variable product page | console.log(error) | you will be able to update the variable product. Please check security gaps in the form
https://localfete.com/products/removeInventory/${id} | EDIT | 200 | edit variable product page | console.log(error) | you will be able to remove one product from inventory
https://localfete.com/products/UpdateInventory | POST | 200 | edit variable product page | console.log(error) | you will be able to update the inventory product. Please check security gaps in the form
https://localfete.com/products/addInventory | POST | 200 | edit variable product page | console.log(error) | you will be able to add a new product to the inventory. Please check security gaps in the form

## Report_Seller
Localfete QA Test-->Report_Seller
Test Case |  | LocalFete | Test Case Description | LocalFate Website QA and Test_Buyer Section |  |  | All Bug Folder |  | Date
Created and Reviewd By |  | Victor | Tested & Reviewed By | Fardin Amin Arpon |  |  | Version: | 1st Release | 2022-03-13 |  | 2022-03-15
Scenario | TestCase Id | Title | Steps/Actions | Data/Endpoint | Response | Expected Result | Actual Result | Bug Doc. | Suggestion
LocalFete QA¦Test Seller Report | Test_01 | check if you can see the total of products, orders and disputes. The design will be changed by tomorrow | 1.Visit the application "EndURL" 2. then cheek all the page review verify | https://localfete.com/seller/admin | 200 | index page | Add market place | photo | Add Go to market place |  | fixed
| Test_02 | check if you can update the profile form and also if there are security gaps | 1. Visit the application "EndURL" 2. cheek link working properly 3. Click on update profile 4. cheek working or not | https://localfete.com/seller/profile | 200 | profile vendor | As Expected add eye icon in update password secton | photo | please add eye icon |  | fixed
| Test_03 | check if you can update the profile store form and also if there are security gaps | 1. Visit the application "EndURL" 2. cheek login link working properly 3. cheek Massage with UI | https://localfete.com/seller/store | 200 | profile store | As Expected update charecter limit | photo | in About Secton we can add more character |  | The limit is ok because otherwise people will have to do scroll and that is something that we don't want to
| Test_04 | after updating the profile store you will be able to see the store page | 1. Visit the application "EndURL" 2. Cheek link working properly or not 3. Cheek UI and All Element | https://localfete.com/stores/vendor/{store_name} | 200 | store page | add new line | photo | it brokes the box area please add new line |  | fixed
| Test_05 | you will se all the products with pagination and also three call actions on the right side: view, edit and delete product | 1. Visit the application "URL" 2. Give register mail data 3. Then a mail come on inbox 4. cheek mail link | https://localfete.com/seller/products | 200 | products page | Fully broken | photo | Box fully broken Give Charecter limit change colour Red |  | fixed
| Test_06 | you will see the single product page it can be simple or variable. Please click in every section including the tabs at the bottom section | 1. Visit the application "URL" 2. Search the item what are looking for | https://localfete.com/products/article/{product_name} | 200 | single product page | Box Broke | photo | Box broken please add Review section Charecter limit |  | fixed
| Test_07 | you will see at the right of every product three buttons: First: Open the product in a new tab second: Edit the product it can be simple or variable Third: Delete the product. Try to delete both type of products | 1. Visit the application "URL" 2.Check homepage | https://localfete.com/seller/editproduct/{product_id} | 200 | Edit Product Page | Broke and add limitation also cheek inventoty section | photo | give limitation also cheek inventoty section | give limitation also cheek inventoty section | fixed
| Test_08 | From seller product page: https://localfete.com/seller/products You will be able to delete any product clicking on the button with trush icon. Please verify if it works with both type of products | 1. Visit the application "URL" 2. Try to create a new user with same mail which already have created 3. it show redirect to the welcome page | https://localfete.com/seller/removeproduct/{product_id} | 200 | Remove Product | As Expected | As expected
| Test_09 | Please create a simple product including gallery and video. Check if there are security gaps in the form | 1. Visit the application "URL" 2. Login in as a buyer user 3. Bought some Itme form store 4. Goto the cart icon 5. look all the item display on the cart | https://localfete.com/seller/productsimple | 200 | create simple product page | Name takes much space add limitataon | bug photo | Name takes much space add limitataon |  | fixed i left the limit 100
| Test_10 | You will be able to create the variable product in two parts: 1. General information. Please check security gaps in the form 2. Add products to the inventory. Please check security gaps in the form | 1. Visit the application "URL" 2. Login in as a buyer user 3. Bought some Itme form store 4. Goto the cart icon 5. look all the item display on the cart | https://localfete.com/seller/productvariable | 200 | create variable product page | takes more area | photo |  |  | fixed
| Test_11 | you will see the seller's orders. On the right side you can download the order and the delivery status. Try to download the order and also open the delivery status | 1. Visit the application "URL" 2. Login in as a buyer user 3. Bought some Itme form store 4. Goto the cart icon 5. look all the item display on the cart | https://localfete.com/seller/orders | 200 | orders page | As Expected | photo |  |  | fixed
| Test_12 | Yu will see the status delivery of the product. Also you will be able to change the status. Try to change the status of the product | 1. Visit the application "URL" | https://localfete.com/seller/statusdelivery/{store_id}/{order_id} | 200 | Delivery Page | As Expected
| Test_13 | You will se the seller's disputes. On the right side you can click the button to see the detail of the dispute. | 1. Visit the application "URL" | https://localfete.com/seller/disputes | 200 | disputes page | As Expected
| Test_14 | You will see the detail of the dispute and also you can reply it. Please check security gaps in the form | 1. Visit the application "URL" | https://localfete.com/seller/disputedetails/{dispute_id} | 200 | dispute detail page | As Expected
| Test_15 | You will be able to delete the seller account | 1. Visit the application "URL" | https://localfete.com/seller/delete | 200 | delete account page | As Expected
| Test_16 | you will be able to update the simple product. Please security gaps in the form | 1. Visit the application "URL" | https://localfete.com/products/updateSimple | 200 | edit simple product page | As Expected
| Test_17 | you will be able to update the variable product. Please check security gaps in the form | 1. Visit the application "URL" | https://localfete.com/products/updateVariable | 200 | edit variable product page | As Expected
| Test_18 | you will be able to remove one product from inventory | 1. Visit the application "URL" | https://localfete.com/products/removeInventory/${id} | 200 | edit variable product page | As Expected
| Test_19 | you will be able to update the inventory product. Please check security gaps in the form | 1. Visit the application "URL" | https://localfete.com/products/UpdateInventory | 200 | edit variable product page | As Expected
| Test_20 | you will be able to add a new product to the inventory. Please check security gaps in the form | 1. Visit the application "URL" | https://localfete.com/products/addInventory | 200 | edit variable product page | As Expected

## Estress Testing
End Point | Method | status | Response | Error | Comments | Bug
https://localfete.com/user/register | get | 200 | Registration page | Console.log (error) | We need a test of 250 users doing log in | 250 people in 30sec working 500=1min 1000=2min 2000=4min 3000=6min 4000=8min 100in 1sec okey 200 in 2 sec is error agter 150 is broke 1min 500 people is okey but 500 people in 5sec broke 100 user 1s = 200ok resopnse (100% working) 150 user 2s (99% working) 200 user 2s Error 40% Stress point is 150
https://localfete.com/user/login | get | 200 | Login Page | Console.log (error) | We need a test of 250 users doing log in
https://localfete.com/stores | get | 200 | Store Page | Console.log (error) | We need a test of 250 users buying products
https://localfete.com/stores | get | 200 | Store Page | Console.log (error) | We need a test of 250 people buying the same product at the same time
https://localfete.com/stores/home/design | get | 200 | home page | Console.log (error) | We need a test of 250 users searching any localtion and any product at the same time
https://localfete.com/seller/productsimple | get | 200 | Registration page | Console.log (error) | We need a test of 250 sellers creating a product simple
https://localfete.com/seller/productvariable | get | 200 | Registration page | Console.log (error) | We need a test of 250 sellers creating a variable product
https://localfete.com/home/design

## Admin Dashboard
End Point | Method | status | response | error | comments
https://localfete.com/admin/ | GET | 200 | home admin | console.log(error) | the home page must show somethin similar to the seller dashboard
https://localfete.com/admin/profile | GET | 200 | profile admin | console.log(error) | check if you can edit and change the password. Leave the initial password after testing
https://localfete.com/admin/categories | GET | 200 | categories | console.log(error) | try to create, edit and delete a category
https://localfete.com/admin/subcategories | GET | 200 | subcategories | console.log(error) | try to create, edit and delete a subcategory
https://localfete.com/admin/stores | GET | 200 | stores | console.log(error) | check if you can open the stores pages
https://localfete.com/admin/events | GET | 200 | events | console.log(error) | create edit and delete an event. Also check if it is display on the marketplace
https://localfete.com/admin/products | GET | 200 | products | console.log(error) | check if you can open the products pages
https://localfete.com/user/logout | get | 200 | home page | console.log(error) | check if you can log out

## Report_Admin
Localfete QA Test-->Report_Admin
Test Case |  | LocalFete | LocalFate Website QA and Test_Buyer Section |  |  | All Bug Folder |  | Date
Created and Reviewd By |  | Victor | Fardin Amin Arpon |  |  | Version: | 1st Release | 2022-03-27
Scenario | TestCase Id | Title | Data/ Endpoint | Response | Expected Result | Actual Result | Bug Doc. | Suggestion
LocalFete QA¦Test Admin | Test_01 | the home page must show somethin similar to the seller dashboard | https://localfete.com/admin/ | 200 | home admin | home admin some bug issue | photo | broke the box please fix it |  | done
| Test_02 | check if you can edit and change the Password. Leave the initial password after testing | https://localfete.com/admin/profile | 200 | profile admin | profile admin | photo |  |  | done
| Test_03 | try to create, edit and delete a category | https://localfete.com/admin/categories | 200 | categories | categories | photo | When we press on the delete btnit not deleted please see this pic and add character limit | When we press on the delete btnit not deleted | done
| Test_04 | try to create, edit and delete a subcategory | https://localfete.com/admin/subcategories | 200 | subcategories | subcategories | photo | it not deleted please see this pic and also add character limit |  | fixed
| Test_05 | check if you can open the stores pages | https://localfete.com/admin/stores | 200 | stores | stores | photo |  |  | done
| Test_06 | create edit and delete an event. Also check if it is display on the marketplace | https://localfete.com/admin/events | 200 | events | events | photo | Also see this pic | Also see this pic | done
| Test_07 | check if you can open the products pages | https://localfete.com/admin/products | 200 | products | products | photo |  |  | done
| Test_08 | check if you can log out | https://localfete.com/user/logout | 200 | home page | home page | As expected

## Bullingdon Digital
End POint | Bug pic
https://bullingdondigital.com/demo-new-03/ | Bug folder pic
Comments:
Please check this landing page in all devices
Also test this landing page at
PageSpeed Insights https://pagespeed.web.dev
Gmetrix.net https://www.gmetrix.net

## Testing_Flow_local_Fete
BUYER EXPERIENCE
Activity | Comments
1. Registration | It works, i got the welcome page and the email notification
2. Activation account via email | It works,when i clicked on the link it open the welcome page
3. Change password from login page | It works, i could update my password from my email account The banner image and colours must be updated in the email notification
Dashboard
1. Home page | it loads the total orders and disputes
1. Profile section | It works, i could update my profile. The validation form is working as well
2. Change Password | It works i could change password from dashboard
3. Orders | I can see the orders, download the orders and see the order detail
4. Order details | I can see the status delivery
5. Disputes | I can create dispute and reply dispute
6. Disputes | Fixed create multiple disputes | done
7. Go to Marketplace link | the link is working
8. Notifications by Bell | i got notifications by bell. When i created an order or when i got a response from a dispute
9. Notifications by emal | I got all notifications when i created an order or when i got a response form a dispute
9. Log out link | It works
10. Delete account | Delete account is not working | done
SELLER EXPERIENCE
1. Registration | It works, i got the welcome page and the email notification
2. Activation account via email | It works,when i clicked on the link it open the welcome page
3. Change password from login page | It works, i could update my password from my email account The banner image and colours must be updated in the email notification
4. Activate Account with Stripe | it works
Dashboard
profile store | update the About: Character limit 246 in the validation it says 250
Update product | The loader is missing when the product is updating | done
Create single product | Display gallery images in the box. The height for the images should be fixed. It is broken | done
Add inventory page and pop up window | add the loader when the inventory is creating | done
orders | verify taxes with Alisha in the UK before doing live test
Bell Notification | bell notification. Verify if once an order is created the seller gets the notification by bell into the dashboard | done
Home page | on the bottom earning graphic the total should be taken from order detail | done
7. Go to Marketplace link | the link is working
8. Notifications by Bell | i got notifications by bell. When an order was created and when a dispute was assigned to me
9. Notifications by emal | I got all notifications when i created an order or when i got a response form a dispute
9. Log out link | It works
10. Delete account | Delete account is not working | done
Marketplace
aside menu all pages | aside menu is not working. It does not open the subcategories
single product page | We have to fix the height of the thumbnails in the gallery
variable product page | updae the inventory button as it is right now in single product page | done
Cart page | fix table border | done
Home Page
logo | looks blurred on google chrome
search borough | add pagination to stores and events

## Council_Dashboard
End Point | Method | status | response | error | comments
https://localfete.com/council/ | GET | 200 | home admin | console.log(error) | the home page must show something similar to the seller dashboard and the information should be dynamic
https://localfete.com/admin/profile | GET | 200 | profile admin | console.log(error) | check if you can edit and change the password. Leave the initial password after testing
https://localfete.com/admin/stores | GET | 200 | stores | console.log(error) | check if you can open the stores pages
https://localfete.com/admin/events | GET | 200 | events | console.log(error) | create edit and delete an event. Also check if it is display on the marketplace
https://localfete.com/admin/products | GET | 200 | products | console.log(error) | check if you can open the products pages
https://localfete.com/user/logout | get | 200 | home page | console.log(error) | check if you can log out

## Report_Council
Localfete QA Test-->Report_Council
Test Case |  | LocalFete | LocalFate Website QA and Test_Buyer Section |  |  | All Bug Folder |  | Date
Created and Reviewd By |  | Victor | Fardin Amin Arpon |  |  | Version: | 1st Release | -620092
Scenario | TestCase Id | Title | Data/ Endpoint | Response | Expected Result | Actual Result | Bug Doc. | Suggestion
LocalFete QA ¦Test Council | Test_01 | the home page must show something similar to the seller dashboard and the information should be dynamic | https://localfete.com/council/ | 200 | home admin | home admin | photo
| Test_02 | check if you can edit and change the password. Leave the initial password after testing | https://localfete.com/admin/profile | 200 | profile admin | profile admin | photo
| Test_03 | check if you can open the stores pages | https://localfete.com/admin/stores | 200 | stores | categories | photo
| Test_04 | create edit and delete an event. Also check if it is display on the marketplace | https://localfete.com/admin/events | 200 | events | subcategories | photo
| Test_05 | check if you can open the products pages | https://localfete.com/admin/products | 200 | products | stores | photo
| Test_06 | check if you can log out | https://localfete.com/user/logout | 200 | home page | events | photo
photo